## Sheet1
S.no. | Interface | Description | Status | Dev comments
1 | register | Customer register> DOB should accept years>1982 | no issue | DOB dropdown load previous 10 year only .
2 | Front | When on the login page and click on home, about us, contact, it is not working | no issue | There is no content in about and contact us page.
3 | email content customer | When any user is approved, Add 2 more line, as it should be same all over. For any help, please contact us at: coffee@hashtaglabs.biz Hope you will have benefit from our services. | enhancement
4 | register | when the user register successfully change the message from "Consultant created successfully" to "consultant registered successfully" same as for Customer registered successfully" | enhancement
5 | Email | When consultant register> on gmail getting UI issue in the template | new
6 | Admin | Add consultant> 2nd screen>> Spelling of Qualification in place holder is wrong | closed
7 | email content consultant | when admin add consultant and customer Add 2 more line, as it should be same all over. For any help, please contact us at: coffee@hashtaglabs.biz Hope you will have benefit from our services. | fixed
8 | Customer/consultant login | remove success message on dashboard | working fine
9 | Customer login | create ticket> Multiple document upload features(as with add more button) | enhancement
10 | Customer login | edit ticket> adjust the UI of the form, same as view ticket UI | UI Issue
11 | Consultant login | Assigned ticket > while assigning the ticket to agent, if there is no agent available, then it should no "no agent" in the Agent name drop down | fixed
12 | Consultant login | Side navigation > agent and its icon is not properly aligned | UI Issue
13 | Consultant login | Add and edit agent> experties UI | UI Issue
14 | Agent login | View ticket> UI of the form should be adjusted | UI Issue
15 | Agent login | when agent chat with the customer> in the customer notification getting "agent details" | fixed | Add Agent before agent name for distiguish b/w consultant and agent
16 | Consultant/customer login | feedback >export button>> rating is not showing | new
17 | Consultant login | when consltant create > its first agent>> that agent is not showing in the list while assigning the ticket to him | new
18 | Admin login | completed ticket> In Export button not getting rating | new
19 | Admin login | Consultant rating > if any consultant doesnot have rating and on view remark show>> message "no remark: | new
20 | Front | consultant list page is missing | new | As of now I create only forms . I will make it.
21 | Front | front page button is not working on "Our Legal Practice Area" > "view more button | no issue | Its dummy connent it will changed in future.
22 | Consultant> add agent | 2nd screen Qualification spelling | new(13/4/2020)
23 | Admin>unassigned ticket>>create ticket | UI of the form | UI Issue
24 | Admin> create ticket | on adding multiple file> show its name with title and place holer for "enter document name" | new
25 | Admin> unassigned ticket | on edit ticket>> UI of the form | UI Issue
26 | Admin> unassigned ticket> add ticket | document upload > view should be adjust as UI | new
27